## Test Cases
TC ID | SDLC Phase | Project Activity | Testing Activity | Purpose / Check | Example / Evidence | Expected Outcome | Actual Result | Status
TC01 | Requirements Analysis | Collect requirements for registration, login, product search, cart and checkout. | Review requirements and acceptance criteria. | Check requirements are clear, complete and testable. | Requirement review checklist | Ambiguities and missing requirements are recorded. | To be completed during practical | Pending
TC02 | Planning | Define project scope, timeline, team roles and risks. | Prepare test plan, testing scope, resources and entry/exit criteria. | Ensure testing is planned before execution. | Test plan document | Testing approach, schedule and responsibilities are documented. | To be completed during practical | Pending
TC03 | System Design | Design pages, database and connections between cart, payment and order modules. | Review design and identify integration test scenarios. | Check data flow and module interactions are considered. | Design review notes / test scenarios | Major interfaces and integration risks are identified. | To be completed during practical | Pending
TC04 | Development / Coding | Implement login, product listing, cart and checkout features. | Prepare test cases and test data; review coverage; support unit testing. | Ensure features have planned checks before system testing. | Test case sheet / test data | Test cases cover key requirements and expected results. | To be completed during practical | Pending
TC05 | Testing | Test complete shopping journeys and individual modules. | Run functional, integration, system and non-functional tests. | Compare actual behaviour with requirements. | Execution log / defect report | Defects are logged clearly and test results are recorded. | To be completed during practical | Pending
TC06 | Testing | Check a reported defect after a code fix. | Retest the defect and run regression tests. | Confirm the fix works and existing features remain stable. | Retest evidence / regression results | Defect is verified or reopened based on the result. | To be completed during practical | Pending
TC07 | Deployment | Release the approved website build to production. | Perform smoke/sanity checks on critical functions. | Confirm the deployed build is usable. | Release checklist | Critical pages and main user journey work after release. | To be completed during practical | Pending
TC08 | Maintenance | Apply updates and resolve issues reported by users. | Verify bug fixes and run regression tests on affected modules. | Prevent new changes from breaking existing functionality. | Change request / regression checklist | Changes are verified and test cases are updated. | To be completed during practical | Pending

## Test Plan
Parameter | Details
Project Name | Online Shopping Website (sample project)
Practical Title | Understand SDLC and STLC phases and identify testing activities during each stage.
Application / Software | E-commerce web application
Objective | To map each SDLC phase to the related testing activities.
Scope | Requirements analysis, planning, design, development, testing, deployment and maintenance.
Testing Strategy | Review requirements and design, prepare test cases, execute functional and non-functional checks, log defects, retest and run regression testing.
Test Environment | Sample web application context; Google Chrome / Windows may be used for practical demonstration.
Entry Criteria | Project requirements and sample application workflow are understood.
Exit Criteria | All SDLC phases and related testing activities are documented in the workbook.
Deliverables | SDLC/STLC activity mapping, test case sheet, test plan and summary.
Assumptions | The online shopping website is a sample project used to explain the life cycle.

## Execution Summary
Metric | Result
Total SDLC Phases Covered | 7
Testing Activities Identified | 8
Executed Application Test Cases | 0
Passed | Not executed – documentation practical
Failed | Not executed – documentation practical
Blocked | 0
Overall Status | Prepared for review
Note | This practical maps life-cycle activities; results should be updated if actual project testing is performed.